## ProductBacklog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | User | Capture the video | I can capture my hand | 1 | RC | 2021-11-29
1 | SB1/US2 | User | Detect my hand | I can use my hand for mouse gestures | 1 | RC | 2021-11-30
1 | SB1/US3 | User | Recognize my hand | I can use my fingers for mouse gestures | 1 | RC | 2021-12-01
1 | SB1/US4 | User | Detect my index finger | I can move cursor | 1 | SG | 2021-12-03
1 | SB1/US5 | User | Use coordinates system | I can control finger movement | 1 | YK | 2021-12-05
1 | SB1/US6 | User | Detect mouse movements in frame rate | I can work in specific range | 1 | YK | 2021-12-07
1 | SB1/US7 | User | Add smoothening effects | I can move cursor smoothly | 1 | SG | 2021-12-09
1 | SB1/US8 | User | Add a feature when a finger other than index finger is up | I can stop cursor movement | 1 | SG | 2021-12-11
1 | SB1/US9 | User | Add fps text on screen | I can see my fps while moving mouse | 1 | YK | 2021-12-12
2 | SB2/US1 | User | Detect my middle finger | I can use that finger to add click gesture | 2 | RC | 2021-12-13
2 | SB2/US2 | User | Find the coordinates of middle finger | I can compare them with the coordinates of index finger | 2 | YK | 2021-12-15
2 | SB2/US3 | User | Find the tip of middle finger | I can add the click gesture | 2 | RC | 2021-12-17
2 | SB2/US4 | User | Find the distance between the tips of index and middle finger | I can use clicking gesture | 2 | YK | 2021-12-19
2 | SB2/US5 | User | Compare the distance with particular value | I can click when distance is less than a particular value | 2 | SG | 2021-12-21
2 | SB2/US6 | User | Add of feature of joining the tips of middle and index finger | I can use the click gesture | 2 | SG | 2021-12-24
3 | SB3/US1 | User | Detect my thumb | I can use volume control gesture | 3 | RC | 2022-02-01
3 | SB3/US2 | User | Recognize my thumb | I can find the landmarks of the tip of thumb | 3 | RC | 2022-02-04
3 | SB3/US3 | User | Recognize the tip of thumb landmark | I can use it with the tip of index finger for controlling volume | 3 | SG | 2022-02-07
3 | SB3/US4 | User | Find the coordinates of the tip of thumb | I can compare them with the coordinates of index finger | 3 | YK | 2022-02-10
3 | SB3/US5 | User | Adjust the distance between the tips of thumb and index finger | I can adjust volume accordingly | 3 | SG | 2022-02-12
4 | SB4/US1 | User | Detect my ring finger | I can create drag and drop gesture | 4 | RC | 2022-02-15
4 | SB4/US2 | User | Detect the land mark of the tip of ring finger | I can find coordinates of ring finger | 4 | SG | 2022-02-18
4 | SB4/US3 | User | Find the distance between the tips of middle and ring finger | I can create single click gesture event | 4 | YK | 2022-02-21
4 | SB4/US4 | User | Add a feature of joining the tips of both the fingers | I can drag and drop an object | 4 | SG | 2022-02-24
4 | SB4/US5 | User | Create an executable file | I can use that on any system | 4 | RC + SG +YK | 2022-02-26

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - AI Virtual Mouse
SB1/US1 | As an User I want to capture the video so that I can capture my hand | SB1/US1/T1 | Capture the video frame | RC | In Progress | 2021-11-29
|  | SB1/US1/T2 | Capture my hand | RC | In Progress | 2021-11-29
|  | SB1/US1/T3 | Display the resulting frame | RC | In Progress | 2021-11-29
SB1/US2 | As an User I want to detect my hand so that I can use my hand for mouse gestures | SB1/US2/T1 | Study of Hand Tracking Module | RC | In Progress | 2021-11-30
|  | SB1/US2/T2 | After studying we use hand detector class object | RC | In Progress | 2021-11-30
SB1/US3 | As an User I want to recognize my hand so that I can use my fingers for mouse gestures | SB1/US3/T1 | Hand placement in front of camera | RC | In Progress | 2021-12-01
|  | SB1/US3/T2 | To move mouse show hand with one index finger up | RC | In Progress | 2021-12-02
SB1/US4 | As an User I want to detect my index finger so that I can move cursor | SB1/US4/T1 | Detect when index finger is up | SG | In Progress | 2021-12-03
|  | SB1/US4/T2 | Show landmarks of the index finger | SG | In Progress | 2021-12-04
SB1/US5 | As an User I want to use coordinate system so that I can control finger movement | SB1/US5/T1 | Study of hand detector object for coordinates | YK | In Progress | 2021-12-05
|  | SB1/US5/T2 | Find Position of the index finger | YK | In Progress | 2021-12-05
SB1/US6 | As an User I want to detect mouse movements in frame rate so that I can work in specific range | SB1/US6/T1 | Make a boundry for movements | YK | In Progress | 2021-12-06
|  | SB1/US6/T2 | Mouse will not work in out of the boundry | YK | In Progress | 2021-12-07
SB1/US7 | As an User I want to add smoothening effects so that I can move cursor smoothly | SB1/US7/T1 | Set smoothning to random value | SG | In Progress | 2021-12-08
|  | SB1/US7/T2 | For smoothning we take the help of coordinates | SG | In Progress | 2021-12-09
SB1/US8 | As a User I want to add a feature when a finger other than index finger is up so that I can stop cursor movement | SB1/US8/T1 | To check if only one finger(index) is up | SG | In Progress | 2021-12-10
|  | SB1/US8/T2 | Stop movement when other finger detected | SG | In Progress | 2021-12-11
SB1/US9 | As an User I want to add fps text on screen so that I can see my fps while moving mouse | SB1/US9/T1 | Study of cv2 library | YK | In Progress | 2021-12-12
|  | SB1/US9/T2 | Use of cv2 library to put text on screen | YK | In Progress | 2021-12-12

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2021-11-29 | 19 | 19 | Tasks
2021-11-30 | 17 | 18
2021-12-01 | 15 | 17
2021-12-03 | 13 | 15
2021-12-05 | 11 | 12
2021-12-07 | 9 | 10
2021-12-09 | 7 | 6
2021-12-11 | 5 | 4
2021-12-12 | 0 | 0
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - AI Virtual Mouse
SB2/US1 | As an User I want to detect my middle finger so that I can use that finger to add click gesture | SB2/US1/T1 | Create the object of hand detector class | RC | In Progress | 2021-12-13
|  | SB2/US1/T2 | Detect the middle finger | RC | In Progress | 2021-12-14
SB2/US2 | As an User I want to find the coordinates of middle finger so that I can compare them with the coordinates of index finger | SB2/US2/T1 | Create the object of the hand detector class | YK | In Progress | 2021-12-15
|  | SB2/US2/T2 | Locate the middle finger | YK | In Progress | 2021-12-16
SB2/US3 | As an User I want to find the tip of middle finger so that I can add the click gesture | SB2/US3/T1 | Study the indices of all finger | RC | In Progress | 2021-12-17
|  | SB2/US3/T2 | Detect the middle finger | RC | In Progress | 2021-12-18
|  | SB2/US3/T3 | Finding tip of middle finger | RC | In Progress | 2021-12-19
SB2/US4 | As an User I want to find the distance between the tips of index and middle finger so that I can use clicking gesture | SB2/US4/T1 | Find the landmarks of the tip of the middle finger | YK | In Progress | 2021-12-20
|  | SB2/US4/T2 | Find landmarks coordinates | YK | In Progress | 2021-12-21
SB2/US5 | As an User I want to compare the distance with particular value so that I can click when distance is less than a particular value | SB2/US5/T1 | Study of math library | SG | In Progress | 2021-12-22
|  | SB2/US5/T2 | Compare the distance of the tip of both fingers | SG | In Progress | 2021-12-23
SB2/US6 | As an User I want to add of feature of joining the tips of middle and index finger so that I can use the click gesture | SB2/US6/T1 | Check the distance between the tips of middle and index finger | SG | In Progress | 2021-12-24
|  | SB2/US6/T2 | Add clicking gesture if distance is less than a particular value | SG | In Progress | 2021-12-24

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task | Tasks
2021-12-13 | 13 | 13
2021-12-15 | 11 | 12
2021-12-17 | 9 | 11
2021-12-19 | 7 | 8
2021-12-21 | 5 | 5
2021-12-24 | 0 | 0

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - AI Virtual Mouse
SB3/US1 | As an User I want to detect my thumb so that I can use volume control gesture | SB3/US1/T1 | Check if fingers are up | RC | Not Started | 2022-01-01
|  | SB3/US1/T2 | Detecting thumb | RC | Not Started | 2022-01-05
SB3/US2 | As an User I want to recognize my thumb so that I can find the landmarks of the tip of thumb | SB3/US2/T1 | Recognize Thumb | RC | Not Started | 2022-01-08
|  | SB3/US2/T2 | Find the landmark of the thumb | RC | Not Started | 2022-01-10
SB3/US3 | As an User I want to recognize the tip of thumb landmark so that I can use it with the tip of index finger for controlling volume | SB3/US3/T1 | Study of Hand detector | SG | Not Started | 2022-01-11
|  | SB3/US3/T2 | Mark the tip of the thumb | SG | Not Started | 2022-01-12
SB3/US4 | As an User I want to find the coordinates of the tip of thumb so that I can compare them with the coordinates of index finger | SB3/US4/T1 | Find the coordinates of the thumb | YK | Not Started | 2022-01-20
|  | SB3/US4/T2 | Check the distance between the coordinates of index finger and thumb | YK | Not Started | 2022-01-22
SB3/US5 | As an User I want to adjust the distance between the tips of thumb and index finger so that I can adjust volume accordingly | SB3/US5/T1 | Study of AudioUtilities and IAudioEndpointVolume library | SG | Not Started | 2022-01-24
|  | SB3/US5/T2 | Adjust volume with the distance of fingers | SG | Not Started | 2022-01-25

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2022-02-01 | 10 |  | Tasks
2022-02-04 | 8
2022-02-07 | 6
2022-02-10 | 4
2022-02-12 | 0

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - AI Virtual Mouse
SB4/US1 | As an User I want to detect my ring finger so that I can create drag and drop gesture | SB4/US1/T1 | Study the indexes of all finger | RC | Not Started | 2022-02-15
|  | SB4/US1/T2 | Detect ring finger | RC | Not Started | 2022-02-16
SB4/US2 | As an User I want to detect the landmark of the tip of ring finger so that I can find coordinates of ring finger | SB4/US2/T1 | Find landmark of the ring finger | SG | Not Started | 2022-02-18
|  | SB4/US2/T2 | Find the coordinates of ring finger | SG | Not Started | 2022-02-20
SB4/US3 | As an User I want to find the distance between the tips of middle and ring finger so that I can create single click gesture event | SB4/US3/T1 | Find distance between middle and ring finger | YK | Not Started | 2022-02-21
|  | SB4/US3/T2 | Compare the tip distance of middle and ring finger | YK | Not Started | 2022-02-22
SB4/US4 | As an User I want to add a feature of joining the tips of both the fingers so that I can drag and drop an object | SB4/US4/T1 | Select the object or icon | SG | Not Started | 2022-02-24
|  | SB4/US4/T2 | If distance is less activate the gesture | SG | Not Started | 2022-02-25
SB4/US5 | As an User I want to create an executable file so that I can use that on any system | SB4/US5/T1 | Study of how to make executable file | RC+YK+SG | Not Started | 2022-02-26
|  | SB4/US5/T2 | Make an executable file | RC+YK+SG | Not Started | 2022-02-27

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2022-02-15 | 10 |  | Tasks
2022-02-18 | 8
2022-02-21 | 6
2022-02-24 | 4
2022-02-26 | 0
Days